## Sheet1
Step # | Step Description | Resource | QC | Status | Note from Lichao | Note from Jie
… | … | … |  | … |  | …
MS project
1 | Jun27--Day 1 )
1.1 | set code for cohort extraction(some questions) | Zhao, Jie | None | In progress |  | Please see the attached table
| 1. identify c('', 'NA', 'unknown', 'ambiguous') as NA | Jie |  | Done
| 2. remove the line with missing baseline_edss_score | Jie |  | Done
| 3. for each cohort, randomly select one line when there are duplicated patient id | Jie |  | Done
| 4. calculate the pre index Dmts in different years | Jie |  | Done
| 5. bucketing the continous variables | Jie |  | In progress
Jie
| Some questions | Jie
| 1.1.1 breaking the continous variables into buckets should be done in each cohort or outside cohort(using all data)? | Jie
| 1.1.2 for "11" = "Aubagio" of idx_rx variable, there is no related pre_rx information, but rx_teri_1-rx_teri_4 can be found in the dataset. | Jie
| 1.1.3 when breaking the continous variables into buckets, in order to avoid the imbalance in each bucket, I am writing function to merge the samll bucket with their neighbour until the size of the bucket reach to the threshold.e.g. 3%. Which cutoff of percentage of the bucket size do you suggest? | Jie
2 | Jun28--Day 2 )
1 | Write function to break the numeric variables into quartile. Actually, those variables should meet the following criterias, | Jie |  | Done
| 1). Be numeric class | Jie
| 2). Unique number > 2 | Jie
| 3). Not included in ("idx_rx", 'gender', 'birth_region', 'init_symptom') which are defined as categorical variable | Jie
2 | Write function to merge the categorical variables, for those variables only neighbor levels can be merged together | Jie |  | Done
3 | Write function to merge the categorical variables for those variables whose levels can be merged according to the size of them. | Jie |  | Done
4 | Write functions to turn to dummy variables | Jie |  | Done
5 | Structure the whole code (not complete) | Jie |  | In Progress
3 | Jun29--Day 3 )
1 | debug cohort code for whole process(occupy most of my time today) | Jie |  | Done
2 | merge the two table(original continous + transformed continous) into one | Jie |  | In progress
3 | create 5 cohort table with 6 response in each cohort table for Zhiyu's spark code test | Jie |  | Done
4 | create 60 tables for each cohort and each response and with V1 and V2
4 | Jun30--Day 4 )
1 | add QC code for | Jie |  | Done
| 1. If the unique patient id line has been selected right | Jie |  | Done
| 2. If the pre Dmts are calculated correctly | Jie |  | Done
| 3. If the variables for dummy transformed are selected right | Jie |  | Done
| 4. For those variables to be transformed into dummy variable, if all the NA value have been replaced | Jie |  | Done
| 5. If those variables to be transformed into dummy variable have been transformed into dummy completely, that is to say, except for 0,1, is there any other value exists for those transformed variables. | Jie |  | Done
| 6. If the variables, idx_dt, firstdt, idxyr, tblcoh, have been removed completely | Jie |  | Done
5 | Jul01--Day 5 )
1 | check variables difference between Ray's updated MS data | Jie |  | Done
2 | extract the important varibles for focus when checking the merging process and quartile process | Jie |  | Done
3 | QC the varibles categories of the important varibles to see if they have un-reasonable ones | Jie |  | Done
4 | for those issue categories, set code to modify them and also do the QC for these specified change | Jie |  | In progress
| Sheet2!A1 | Jie |  | In progress
1 | Lichao's result - emr-rwes-pa-spark-dev-datastore/lichao.test/Results/DS_20160705_020408/DS_B2B
2 | Lichao's new 5 cohort after merging transf and withoutTransf together:emr-rwes-pa-spark-dev-datastore/lichao.test/MS_Data/July04/2016-07-05 02.42.49
6 | Jul04--Day 6 )
7 | Jul05--Day 7 )
8 | Jul06--Day 8 )
9 | Jul07--Day 9 )
1 | Generate data for these experiments for sensitivity analysis(different seed) and QC | Jie |  | Done
2 | go through Lichao's elastic net code and get myself be familiar with them | Jie |  | Done

## Sheet2
Variable(2016Jun30) | Definition | Checking progress
idx_rx | Index medication - note that '04' through '07' are all interferons | Find a bug in complicated cohort and add QC code to see if the bug is fixed (fixed!)
gender | gender | No need to adjust
age | Age at index | need to modify to integer margin and after adjust the margin, do the QC to see if the categories > threshold(10%)(completed!)
birth_region | Birth Region | No need to adjust
baseline_edss_score | Baseline EDSS score (may be missing) | No need to adjust
last_cranial_num | Brian MRI T2 lesions closest to index (may be missing) | need to change the Chinese value
last_spinal_num | Spinal MRI T2 lesions closest to index (may be missing) | No need to adjust
switch_rx_dayssup | Days supply for pre-index med (for switch cohorts) | No need to adjust
precont_dayssup | Days supply prior to index for index med (for BRACE continuing cohort) | No need to adjust
years_diag_idx | Years since RRMS diagnosis as of index year (may be missing) | No need to adjust
pre_dmts | new added | ContiCohort & complicatedCohort:1 category for pre_dmts_*(in progress)

## Sheet3
Sever | Location | Note
`100 | F:\Jie\MS\02_Code\MS_InitModel\Results\2016-07-12 14.54.21 | without add new variable groups
`100 | F:\Jie\MS\02_Code\MS_InitModel\Results\2016-07-13 09.40.46 | init_symptom
`100 | F:\Jie\MS\02_Code\MS_InitModel\Results\2016-07-13 10.18.25 | Relapse_pre0_psev3
`100 | F:\Jie\MS\02_Code\MS_InitModel\Results\2016-07-13 10.42.46 | Pre0_qdeg_disab
`100 | F:\Jie\MS\02_Code\MS_NonRegularisedGLM\Results\2016-07-14 06.10.58 | GLM(without constained Glm Net) with top 10 variables from Glmnet
`100 | F:\Jie\MS\02_Code\MS_InitModel\Results\2016-07-14 07.17.09 | Glmnet with top 10 variables from glmnet(F:\Jie\MS\02_Code\MS_InitModel\Results\2016-07-12 14.54.21)
2016-07-15
`100 | F:/Lichao/work/Projects/MultipleSclerosis/Results/2016-07-14/2016-07-14 20.48.49/ | ENetModelDir
`100 | F:/Jie/MS/02_Code/MS_InitModel/Results/2016-07-15 02.33.53/ | subVarsENetModelDir
`100 | F:/Lichao/work/Projects/MultipleSclerosis/Results/2016-07-14/2016-07-14 22.26.06/ | GlmModelDir
`100 | F:\Jie\MS\02_Code\MS_CreateFinalTables\Results\2016-07-15 08.32.18 | Final Tables 1-4
2016-07-19
1 | regenerate cohort data for descriptive stats using new buckets of edss score
input1:inputDir <- "F:/Lichao/work/Projects/MultipleSclerosis/Results/2016-07-05/cohortDt_jie_July06/"
output1:F:\Jie\MS\02_Code\MS_ReExtractCohorts_4Descriptive\Results\2016-07-19 01.52.43
2 | QC the data obtained above
3 | update the descriptive table of variable definition