## Sheet1
Status | Taskforce | Tasks | Milestone | Deadline
[5 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7
 | time axis 2015-11-09 to 2015-12-27
| Zhenxing (BJ) | HAE patients predictors derivation | Data extracted | 2015-11-09 | bar: 2015-11-09
| Nadea, Dong | HAE patients profiling | potential criteria from HAE profiling | 2015-11-12 | bar: 2015-11-10 to 2015-11-12
| Zhenxing (BJ) | Matching Non-HAE patients | Data extracted | 2015-11-12 | bar: 2015-11-10 to 2015-11-12
| Nadea, Dong | Non-HAE patients profiling | report % of non-HAE pats with the interested criteria from HAE profiling | 2015-11-13 | bar: 2015-11-13
| Dong | ML algorithms details | draft details sent | 2015-11-10 | bar: 2015-11-10
| Dong, John, Nadea | ML algorithms discussion & decision (ML-0, ML1-A,B,C) | final details sent | 2015-11-12 | bar: 2015-11-10 to 2015-11-12
| Dong, John, Nadea | Stratification approach discussion & decision | final details sent | 2015-11-17 | bar: 2015-11-16 to 2015-11-17
| Dong | ML-0: feature selection with bagging LASSO/under sampling random forest | feature selected | 2015-11-13
| Jie/Hui (BJ) | ML-1A: bagging biased SVM | model built | 2015-11-29
| Dong | ML-1B: bagging RF | model built | 2015-11-29
| Jie/Hui (BJ) | ML-1C: bagging biased SVM with stratified sample | model built | 2015-11-29
| Dong, Jie/Hui (BJ) | Model evaluation, add extra HAE patients, re-run best model | best model built | 2015-11-30
| Zhenxing (BJ) | Scoring sample derivation | Data extracted | 2015-11-18 | bar: 2015-11-13; 2015-11-16 to 2015-11-18
| Zhenxing (BJ) | HCP association derivation (require association rule agreed) | Data extracted | 2015-11-24 | bar: 2015-11-19 to 2015-11-20; 2015-11-23 to 2015-11-24
| Jie/Hui (BJ), Dong | Scoring sample with probability of HAE | apply models | 2015-12-02 | bar: 2015-12-01 to 2015-12-02
| Dong | HCP targeting with HAE pats | apply association and scores | 2015-12-04 | bar: 2015-12-03 to 2015-12-04
| Dong, Nadea | Review of models, initial output | identify any problems | 2015-12-07 | bar: 2015-12-03 to 2015-12-04; 2015-12-07 to 2015-12-08
| Jie/Hui (BJ), Dong | Re-run model | bar: 2015-12-08 to 2015-12-10
| Dong, Nadea | Review of final output | identify any problems | 2015-12-10 | bar: 2015-12-09 to 2015-12-11