|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| cid:image001.png@01CE8EB0.21494000    Meeting Notes | | | | | | |
|  | |  |  | |  | | |
|  | | | | | | |
| Meeting Date | 10/14/2015 | | | | | |
| Meeting Time | 11.30 AM | | | | | |
| Project Name | Shire Rare Disease HAE Targeting | | | | | |
| Meeting Purpose | Internal meeting | | | | | |
| Attendees | Dai, Dong (Plymouth Meeting 2); Cai, Yong (Plymouth Meeting 2); Nguyen, John (Plymouth Meeting 2); Daniel, Anu K.(Plymouth Meeting 2); Rigg, John (London); Pitcher, Ashley (London); Schultz, Brian (Plymouth Meeting) | | | | | |
|  | | | | | | |
| |  | | --- | | Agenda |  |  | | --- | | * Internal meeting |  |  | | --- | |  | | | | | | | |
|  | |  | |  | | |
| Brief Meeting  Summary | | | | | | |
| * Full data of HAE patients will be pulled by end of this week (~ 10/16/2015) * Following this, look-back period and HAE sample size will be determined by Dong, John, Anu * There is a delay in confirming the predictors due to Shire sending new publications about HAE misdiagnoses on 10/12/15, Diane (clinical) will review these and send us the updated codes by end of this week or early next week, however the team agrees that this won’t impact our timelines and that we are in good shape | | | | | | |
| Action items | | Person responsible | | | | Deadline |
| Ask Diane (clinical) if there will be new complicated predictor variables due to additional inputs from Shire about HAE misdiagnoses | | Anu | | | | 14/09 (already done) |
| Send to the team most updated methodology doc | | Dong | | | | 10/14 COB |
| Send to Shire an email to validate methodology walk-through date, statement that we are currently reviewing their publications to update our list of predictor variables, set up weekly meetings for November, etc. | | Brian | | | | 10/14 |
| Send to the team the client-friendly methodology document with the following 3 parts:   1. building the modeling dataset (cohort selection/predictors/lookback/ decision on eligibility/stability/etc.) 2. modeling techniques (high level overview) 3. model application/physician scoring/reporting | | Dong, Yong, John | | | | 10/19 |
| Review the methodology document and highlight important areas | | Anu, John, (Nadea) | | | | 10/21 |